## Sheet1
Task ID | Task Name | Start Date | Duration | End Date | Progress | Owner | Status
TSK-001 | Dyson V15 Cyclone Engine Optimization | 2026-07-01 | 15 | 2026-07-16 | 80 | Engineering Team | In Progress
TSK-002 | Supersonic Hair Dryer Noise Reduction | 2026-07-10 | 20 | 2026-07-30 | 45 | Acoustics Team | In Progress
TSK-003 | 360 Vis Nav Robot Vacuum Pathing | 2026-07-18 | 12 | 2026-07-30 | 10 | Software Team | In Progress
TSK-004 | Airstrait Straightener Thermal Control | 2026-07-25 | 8 | 2026-08-02 | 0 | Thermal Team | Not Started